## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2215-swen-261-02-f-7InTheMorning
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page.
As a user I want to be able to create an account to be able to keep my information private and secure | Given that I am on the e-store site when first opening or returning, then I must see a sign in/create user page
As an administrator I want to be able to add and delete products from the store to keep the inventory up to date | Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available.
As a user I want to be able to search a list of products to find specfically what I am looking for | Given that I am viewing a list of products in the inventory, then I must be able to search for specific items from said list
As an administrator I want to be able to edit the quantity of each product to keep the inventory up to date | Given that I am viewing a product, then I should be able to update the quantity of said product.
As a user I want to be able to add items to a cart so I can buy them at any time | Given that I am on the e-store site when I am on the products page then I must be able to add products to my shopping cart
As a user I want to be able to sign into my account and have my shopping cart items saved so I can save the items I want and buy them later | Given that I sign out of the e-store site, when I sign back in, then the items I put in the cart before logging out should be there when I sign back in.
As an admin I want to be able to sign into my account and have my admin privilege to view and edit the inventory and product list | Given that I sign in with an username and password of an admin account, when I sign in I will have the privilege of an admin